# Project Plan Evaluation

## HPAS referral pathway - Advanced Information Systems Development

Original plan, revised plan and actual progress, compared against the evidence in the repository.

# 1. Purpose and sources

This document compares the plan the group made at the start with the plan it actually worked to, and with what was delivered. It is written against the eight dimensions named in the brief: scope, priorities, estimates, task allocation, dependencies, risks, integration and sprint outcomes.

Sources, all of them the group's own artefacts rather than a reconstruction:

| Source | What it contains | Used for |
| --- | --- | --- |
| Part2_Deliverables_List | 17 deliverables D-01 to D-17 with related requirements, dependencies, due date (Day 2 to Day 7) and acceptance criteria | scope, priorities, dependencies, estimates, integration |
| Part3_Product_Backlog | 18 backlog items PB-01 to PB-18 mapped to business rules BR-01 to BR-36 and open question OQ-01 | scope, priorities |
| Agile Workshop notes | stakeholders, the twelve candidate processes, five dependency types, agile strengths and weaknesses | scope, dependencies, risks |
| Task allocation sheets (two versions) | the original four-way split by module, and the revised split (members 3 and 4 re-balanced) | task allocation |
| Acceptance test plan | initial test cases | estimates (indirectly), integration |
| Repository history and CHANGES.md | the two releases and what changed in each | actual progress, sprint outcomes |

# 2. The plan of record

## 2.1 Deliverables and dates

The plan was expressed as seventeen deliverables with day-level deadlines, an explicit dependency chain and an acceptance criterion for each. The chain is D-01 to D-02 to D-03, then D-04 and D-05 in parallel, then the module deliverables, then testing, documentation and the demonstration.

| Deliverable | Due | Depends on | Deliverable | Due | Depends on |
| --- | --- | --- | --- | --- | --- |
| D-01 Stakeholder analysis | Day 2 | - | D-10 Clinic letter module | Day 5 | D-04, D-05 |
| D-02 Business process model | Day 2 | D-01 | D-11 Enquiry management | Day 6 | D-04, D-05 |
| D-03 Requirements specification | Day 3 | D-02 | D-12 Audit and security | Day 6 | D-04, D-05 |
| D-04 System architecture | Day 3 | D-03 | D-13 Management reporting | Day 6 | D-04, D-05 |
| D-05 Database design | Day 3 | D-03 | D-14 Integration test report | Day 6 | all modules |
| D-06 Referral module | Day 4 | D-04, D-05 | D-15 User acceptance test | Day 7 | D-14 |
| D-07 Appointment module | Day 4 | D-04, D-05 | D-16 System documentation | Day 7 | all |
| D-08 Treatment module | Day 5 | D-04, D-05 | D-17 Project demonstration | Day 7 | all |
| D-09 Funding and payment | Day 5 | D-04, D-05 |  |  |  |

The backlog added an eighteenth item, PB-18 "investigate enquiry urgency rules", tied to open question OQ-01 - the one item in the plan that was explicitly a research task rather than a build task.

## 2.2 Original task allocation

| Member | Modules | Data layer and API | Workers |
| --- | --- | --- | --- |
| Member 1 | P1 referral intake, P2 clinical review | Referral, Patient, ClinicalDecision; recordReferral, recordCompletenessCheck, recordSupplement, recordClinicalDecision; /api/db/referrals, /api/db/decisions; SQL 1 and 8 | ReferralWorkers, GpPoolWorkers, ClinicalReviewWorkers, PartnerPoolWorkers |
| Member 2 | P3 scheduling, P4 notification, plus the database configuration | Appointment; upsertAppointment; /api/db/appointments, summary, health, overview; SQL 13; application.properties (H2 file database, port 8090, ddl-auto) | SchedulingWorkers, SchedulingPoolWorkers, NotificationWorkers |
| Member 3 | P7 funding, P12 payment, duplicate-payment rule | FundingCase, Payment; recordFunding, recordPayment, hasSuccessfulPayment, paymentCount; /api/db/payments, /api/db/funding; SQL 5, 6, 7, 9 | FundingWorkers, FunderPoolWorkers, PaymentWorkers, PspPoolWorkers |
| Member 4 | P10 letter, P8 enquiry, audit, roles, shared utilities | ClinicLetter, Enquiry, ProcessAudit, AppUser, UserRole; recordLetter, recordEscalation, recordEnquiry, audit, auditOnly, auditCount; Values, JobContext, DatabaseSeeder; /api/db/letters, enquiries, audit, audit/{key}, chain/{key}; SQL 3, 4, 10, 11, 12; ER diagram and database documentation | LetterWorkers, EnquiryWorkers |

## 2.3 Revised task allocation

A second version of the allocation moved two modules between members 3 and 4:

| Member | Original | Revised | What changed and why |
| --- | --- | --- | --- |
| Member 3 | P7 funding and P12 payment, with the duplicate-payment rule | P7 funding and P10 clinic letter | Gave up payment (the heaviest rule work) and took the letter process, which fits the funding-to-letter handover in the pathway |
| Member 4 | P10 letter, P8 enquiry, audit, roles, shared base | P8 enquiry and P12 payment, plus the audit table | Took payment and kept the audit table, so the two horizontally-used pieces (payment idempotency and the audit trail) sit with one owner |

The re-balance is defensible on integration grounds: the audit table is written by every worker, so whoever owns it also owns the widest cross-cutting concern; pairing it with payment - the one module with a hard uniqueness rule - concentrates the two riskiest areas in one member rather than spreading them. It is less defensible on load: member 4 ends up with two business modules plus the shared base, while member 3 drops to one module.

# 3. Actual progress

Work ran in two releases rather than in the seven-day sequence the plan assumed. The first release delivered the models, forms and workers; the review then produced five points, and the second release answered them and added the persistence layer, the documentation and the evidence.

| Deliverable | Planned | Actual | Verdict |
| --- | --- | --- | --- |
| D-01 Stakeholder analysis | Day 2 | i* SD model: 13 actors, 32 dependencies; stakeholder list in the workshop notes | Delivered |
| D-02 Business process model | Day 2 | 9 BPMN models (15 process definitions), translated to English, structurally checked | Delivered |
| D-03 Requirements specification | Day 3 | Business rules in the case pack plus the requirements traceability table (26 requirements) in the revision | Delivered (late) |
| D-04 System architecture | Day 3 | No separate document; the architecture is visible in the package layout and the worker organisation | Partly |
| D-05 Database design | Day 3 | 11 entities, 11 repositories, ER diagram and database README, delivered in the revision | Delivered (late) |
| D-06 Referral module | Day 4 | P1: registration, completeness check, supplement loop, handover | Delivered |
| D-07 Appointment module | Day 4 | P3 scheduling with the external service, P4 notification with retry | Delivered |
| D-08 Treatment module | Day 5 | Not modelled operationally (assessment and consent, treatment booking and delivery were left out) | Not delivered |
| D-09 Funding and payment | Day 5 | P7 funding and P12 payment, with the duplicate-payment rule enforced in the database | Delivered |
| D-10 Clinic letter | Day 5 | P10 with the seven-day target and escalation | Delivered |
| D-11 Enquiry management | Day 6 | P8 routing with triage | Delivered |
| D-12 Audit and security | Day 6 | Audit row per step, unique per instance/job/action; role groups on every user task | Delivered (late) |
| D-13 Management reporting | Day 6 | 14 documented SQL statements; no reporting interface | Partly |
| D-14 Integration test report | Day 6 | The acceptance criteria evaluation plus machine-readable verification reports, in the revision | Delivered (late) |
| D-15 User acceptance test | Day 7 | Acceptance criteria evaluation with 18 tests and 8 recorded failures; no testing with real users | Partly |
| D-16 System documentation | Day 7 | README, change record, database documentation, i* model guide, all in English | Delivered |
| D-17 Project demonstration | Day 7 | 13-slide presentation, deployment and demonstration scripts, verified end to end | Delivered |

# 4. Critical comparison

| Dimension | What the plan said | What happened | Assessment |
| --- | --- | --- | --- |
| Scope | 17 deliverables, 18 backlog items mapped to BR-01 to BR-36 | Thirteen of the seventeen fully delivered, three partly, one not at all; the backlog's PB-18 (enquiry urgency) was answered in P8 | Scope was realistic for the modules that were built, but it assumed a treatment module that never started. The gap was known late, not early. |
| Priorities | Ordered by the dependency chain: analysis, then model, then requirements and design, then modules | Modules were built first and the design artefacts followed; the requirements specification and database design only arrived in the revision | The order was inverted. Building before the database design existed is what made the fourth review point necessary. |
| Estimates | Day-level due dates; no effort estimates, no story points, no velocity | Work ran in two releases across far more than seven days; the review round alone added a substantial amount | The estimate was a deadline, not an estimate. Nobody could tell whether Day 6 was achievable, so slippage was invisible until the review. |
| Task allocation | Four members by module, then re-balanced between members 3 and 4 | Both versions existed; the revised one concentrated payment and audit with member 4 | The original split followed the pathway, which is a natural boundary. The revision improved integration but worsened balance, and neither version recorded an owner for the cross-cutting work (documentation, evidence, repository). |
| Dependencies | Explicit column in the deliverables list; five dependency types in the workshop notes | The external dependencies (scheduling, correspondence, funding, payment) were modelled as message flows and pools | The internal dependencies were well understood. The dependency on the review itself was not planned for at all. |
| Risks | None registered; the workshop notes list agile weaknesses in general terms | Four real defects surfaced and were fixed (unsafe conditions, reversed i* dependencies, a mis-targeted contribution link, silent date-parsing fallback); two risks remain open (duplicated workers, single-file database under load) | This is the weakest part of the plan. A one-page risk list would have surfaced at least the duplicated-worker risk before the review. |
| Integration | PB-14 integration testing at Day 6, after all modules | Integration was continuous: the workers were wired into one shared project and the persistence layer was added across all 31 workers at once | Integration was handled better than planned. Doing it as a phase after every module would have hidden the duplicate-payment and persistence problems until much later. |
| Sprint outcomes | The workshop notes recommend delivering by sprint; no sprint was defined | Two releases: the first submitted package, then the revision responding to the review, each with its own verification round | Two ad-hoc releases are not sprints, but they did provide a demo-able increment and a feedback loop. With a defined sprint length the review points would have arrived earlier. |

# 5. What the plan got right and wrong

Right:

The dependency chain followed the pathway, so every member could own an end-to-end slice rather than a layer.

Each deliverable carried a stated acceptance criterion, which made the later acceptance evaluation possible.

The backlog was mapped to individual business rules, so scope could be traced back to the case study.

Wrong:

No effort estimates, so the schedule was an aspiration: Day 5 for a treatment module was never plausible.

No risk register, so the two risks that actually bit (duplicated workers; a silent date-parsing fallback) were handled reactively.

No sprint length and no review cadence, so the five review points arrived as a surprise at the end rather than as an early correction.

No owner for the cross-cutting work (evidence, documentation, repository), which is why it all had to be assembled in the last days.

# 6. What we would do differently

Estimate in relative units and re-estimate after the first increment; record the difference, because that number is the real velocity.

Keep a risk list with an owner and a trigger for each item, reviewed at the end of each increment.

Define a sprint length and a demo date, so feedback arrives while there is still room to act on it.

Assign the cross-cutting deliverables (repository, evidence, documentation) to a named owner at the start, not at the end.

Front-load the one artefact that constrained everything else: the database design. It is the reason the fourth review point existed.