## 工作表1
Deliverable | Related Requirement(s) | Dependencies | Due Date | Acceptance Criteria
D-01 Stakeholder Analysis Report | BR-01–BR-36, OQ-01 | Case study, BR register | Day 2 | Identifies all internal and external stakeholders; explains their goals, dependencies and conflicts
D-02 Business Process Model (BPMN) | BR-01–BR-14, BR-28–BR-32 | D-01 | Day 2 | Covers referral, review, booking, treatment, payment, correspondence and enquiry processes; includes at least 4 exception paths
D-03 Requirements Specification | BR-01–BR-36, OQ-01 | D-02 | Day 3 | Includes functional requirements, non-functional requirements, business rules and assumptions; covers BR-01–BR-36
D-04 System Architecture Design | BR-33–BR-36 | D-03 | Day 3 | Includes component diagram, deployment diagram, integration points and security architecture
D-05 Database Design | BR-03, BR-15, BR-21, BR-34, BR-35 | D-03 | Day 3 | Includes ER diagram, table structures, relationships and audit tables
D-06 Referral Management Module | BR-01–BR-04 | D-04, D-05 | Day 4 | Supports referral receipt, document checking, clinical review and decision recording
D-07 Appointment Management Module | BR-10–BR-13, BR-28–BR-29 | D-04, D-05 | Day 4 | Supports appointment identification, confirmation, contact recording, follow-up and cancellation
D-08 Treatment Management Module | BR-05–BR-09, BR-13 | D-04, D-05 | Day 5 | Supports treatment requests, coordination, modification and cycle review
D-09 Funding and Payment Module | BR-14–BR-22 | D-04, D-05 | Day 5 | Supports funding determination, payment requests, refunds and exception handling
D-10 Clinic Letter Module | BR-23–BR-27 | D-04, D-05 | Day 5 | Supports letter preparation, approval, distribution, delay monitoring and escalation
D-11 Enquiry Management Module | BR-30–BR-32, OQ-01 | D-04, D-05 | Day 6 | Supports enquiry recording, classification, routing and resolution
D-12 Audit and Security Module | BR-33–BR-36 | D-04, D-05 | Day 6 | Supports authentication, RBAC, audit logging and non-editable records
D-13 Management Reporting Module | BR-26, BR-29, BR-31, BR-34 | D-06–D-12 | Day 6 | Includes reports on referral volumes, waiting times, delayed letters, unresolved enquiries, payment exceptions and refunds
D-14 Integration Test Report | BR-01–BR-36, OQ-01 | D-06–D-13 | Day 6 | All modules integrated and tested; records test cases, results and defects
D-15 User Acceptance Test Report | BR-01–BR-36, OQ-01 | D-14 | Day 7 | UAT passed; records test scenarios, results and feedback
D-16 System Documentation | BR-01–BR-36, OQ-01 | D-06–D-13 | Day 7 | Includes user manual, administrator manual and API documentation
D-17 Project Demonstration | BR-01–BR-36, OQ-01 | D-15, D-16 | Day 7 | Demonstrates the integrated increment; shows completed tasks, unfinished tasks, key decisions and testing evidence